## Sheet1
| Change Number | Category | Priority | Phase | Title_x | Description | Kcb Dept | Kcb Parent Dept | Service | Change Requester | Assignment Group | Assignee | Open Time | Update Time | Updated By | Aging | Status | Reason for Change | Tribe | Scrum | Status2 | Milestone | Comment | ID | Work Item Type | Title_y | Assigned To | State | Tags
0 | C05242 | Normal Change | 4 - Can Work | Design | INTEGRATE KCB BURUNDI ATMs and POS infrastructure with BI SWITCH | Kindly assist to integrate KCB Burundi ATMs and POS infrastructure with BI SWITCH. Kind Regards | Channels | Subsidiary - Burundi | Transaction Banking | Tychique Nijimbere | Scrum Leads | Kevin Njagi Ndegwa | 2021-04-29 | 2023-10-23 | Ishmael Gwama Mvurya | 1254 | Active | Regulatory requirement (Regulatory notice or approval from O | Clean Up |  | Clean Up Validation |  | In Development | 4085 | User Story | C05242 - KCBB BISWITCH INTEGRATION | Armel Harabarishize <BDI80059@kcbgroup.com> | UAT | September Sprint A
1 | C06315 | Normal Change | 4 - Can Work | Design | AUto Reversals of Failed Vooma Loan Repayments | Please look into the issue of failed Vooma Loan repayments, can they be auto reversing for customers to re initiate. Over the weekend like Friday they have to wait till we receive reconciliation exceptions to reverse find samples below 20220307 3,764.00 C Their DFS.- VOOMA MOBILOAN T24 REPAYMENT KES 254710181371 MM22066POS146 1117107051 FT22066L1YK4 20220307 5,000.00 C Their DFS.- VOOMA MOBILOAN T24 REPAYMENT KES 254712115789 MM22066RL2CN3 1174122277 FT22066YBWBN 20220307 6,414.60 C Their DFS.- VOOMA MOBILOAN T24 REPAYMENT KES 254716175866 MM22066XNLLY3 1105519635 FT22066GWLZ3 20220307 7,269.88 C Their DFS.- VOOMA MOBILOAN T24 REPAYMENT KES 254702548637 MM22066FPYG23 1180047230 FT220665J45N 20220307 10,691.00 C Their DFS.- VOOMA MOBILOAN T24 REPAYMENT KES 254723242318 MM22066VB3O93 1122766637 FT22066R7TC5 20220307 12,829.20 C Their DFS.- VOOMA MOBILOAN T24 REPAYMENT KES 254722813373 MM22066SYRXN3 1104653931 FT22066Q7S2Y | DFS-Operation | Shared Services | Mobi Loan | Nyawera, Marion | Scrum Leads | Otieno, Godfrey Okoth | 2022-03-10 | 2023-10-04 | Minjire, Simon Kibe | 939 | Active | Business Change or Need | Clean Up |  | Clean Up Validation |  |  | 2720 | User Story | C06315 - Auto Reversals of Failed Vooma Loan Repayments | Michael, Chesseto Tung <KEN23301@kcbgroup.com> | Blocked | August A; July Sprint A; July Sprint B; July Sprint C
2 | C06441 | Normal Change | 4 - Can Work | Design | INTEGRATTION OF CUSTODY PLUS AND T24 THROUGH DARAJA | Kindly approve the required changes to fix an issue as per the attached email, sklangat, 10391 | Custody Services Operations | Shared Services | Custody 2000 | Langat, Stephen Kipkoech | Scrum Leads | Matengo, Davis Obonyo Ochieng | 2022-04-21 | 2023-10-04 | Minjire, Simon Kibe | 897 | Active | Business Change or Need | Clean Up | Application | Clean Up Validation |  |  | 3136 | User Story | C06441- INTEGRATION OF CUSTODY PLUS AND T24 THROUGH DARAJA | Otieno, Godfrey Okoth <KEN23249@kcbgroup.com> | Removed
3 | C06441 | Normal Change | 4 - Can Work | Design | INTEGRATTION OF CUSTODY PLUS AND T24 THROUGH DARAJA | Kindly approve the required changes to fix an issue as per the attached email, sklangat, 10391 | Custody Services Operations | Shared Services | Custody 2000 | Langat, Stephen Kipkoech | Scrum Leads | Matengo, Davis Obonyo Ochieng | 2022-04-21 | 2023-10-04 | Minjire, Simon Kibe | 897 | Active | Business Change or Need | Clean Up | Application | Clean Up Validation |  |  | 4952 | User Story | C06441- INTEGRATION OF CUSTODY PLUS AND T24 THROUGH DARAJA | Otieno, Godfrey Okoth <KEN23249@kcbgroup.com> | Development
4 | C06990 | Normal Change | 4 - Can Work | Design | Daraja Authorizing transactions despite existing locks | Daraja Authorizing transactions despite existing locks | I.T Digital Channels | KCB - Information Technology | Mobee | Stanley Nguma | Scrum Leads | Otieno, Godfrey Okoth | 2022-12-05 | 2023-10-17 | Minjire, Simon Kibe | 669 | Active | Error Correction or Fixes ( RCA required ) | Clean Up |  | Clean Up Validation |  |  | 2667 | User Story | C06990 - Daraja Authorizing transactions despite existing locks | Grace Wambui Kiguru <KEN20805@kcbgroup.com> | Analysis/Design | August A
5 | C06995 | Normal Change | 4 - Can Work | Design | EQMS Virtual Ticketing through WhatsApp | Since introduction of EQMS, branches have recorded improved customer service provision with NPS moving from 24 to 64 (H1 results) post implementation, branches are currently serving customers with few resources. Service is also more pro-actively managed. The EQMS has also been crucial in the provision of customer data for the NPS surveys and verbatim feedback on our branch services. There have been areas that require improvement particularly in the error rate of customer data entry. The result is several NPS messages being inadvertently misrouted to non-KCB customers. This has an impact on the sample size of customers and branch reputation of KCB. In line with the strategic pillars of excellence in customer experience and driving operational efficiency, request proposes to rollout EQMS WhatsApp ticketing solution to our branches Key Objectives: 1. To digitize and improve customer experience at our branches. 2. To enhance COVID protocols / social distancing at our banking halls through contactless solution 3. To give our customers optimal convenience through self-serve mobile solutions 4. To have real time feedback / surveys through WhatsApp We therefore seek your approval to carry out PoC for EQMS WhatsApp ticketing solution. This will require installation of the application and database on servers within our LAN, please refer to attached documents. | I.T Business Productivity | KCB - Information Technology | EQMS | Mutai, Richard Kipkoech | Scrum Leads | Otieno, Godfrey Okoth | 2022-12-07 | 2023-10-17 | Minjire, Simon Kibe | 667 | Active | Business Change or Need | Clean Up |  | Clean Up Validation |  |  | 2628 | User Story | C06995 - EQMS Virtual Ticketing through WhatsApp | Grace Wambui Kiguru <KEN20805@kcbgroup.com> | Deployment
6 | C07122 | Normal Change | 4 - Can Work | Design | Mandatory Supporting Documents for iBank Transactions | Please implement mandatory supporting documents for iBank Transactions as per Board approval | Information Technology | Subsidiary - Uganda | Internet Banking System | Jimmy Kisomba | Scrum Leads | Gitau, Kevin | 2023-02-08 | 2023-10-05 | Okodo, James | 604 | Active | Regulatory requirement (Regulatory notice or approval from O | Channels and Cards |  | Allocated to Tribe |  | Valid | 2799 | User Story | C07122-Mandatory Supporting Documents For iBank Transactions | Arthur Joseph Kinyanjui <KEN21811@kcbgroup.com> | Development | August A; iBank Enhancement; July Sprint A; July Sprint B; July Sprint C; UG; Vendor
7 | C07307 | Normal Change | 4 - Can Work | Design | Implementation of Knowledge Management Tool | Implementation of Knowledge Management Tool (Knowledgebase) for centralized collaboration and sharing of knowledge documents | Service Delivery | KCB - Information Technology | Knowledge Management | Maina, Jackline Wanjira | Scrum Leads | Otieno, Godfrey Okoth | 2023-03-27 | 2023-10-17 | Minjire, Simon Kibe | 557 | Active | Project | Clean Up |  | Delivered | Delivered |  | 2620 | User Story | C07307 - Implementation of Knowledge Management Tool | Caroline Kathaaara <ken10904@kcbgroup.com> | Blocked
8 | C07312 | Normal Change | 4 - Can Work | Design | Log4j Vulnerabilities as at 24th March 2023 | Please find attached Lg4j Vulnerabilities and assist resolve. | I.T Digital Channels | KCB - Information Technology | all channels | Halima Saadia | Scrum Leads | Otieno, Godfrey Okoth | 2023-03-27 | 2023-10-17 | Minjire, Simon Kibe | 557 | Active | 0 | Channels and Cards |  | Allocated to Tribe |  |  | 2581 | User Story | C07312 - Log4j Vulnerabilities tests | Otieno, Godfrey Okoth <KEN23249@kcbgroup.com> | Analysis/Design
9 | C07391 | Emergency Change | 3 - Can work with minor issues | Change Manager | UTILIZATION OF LOCKED AMOUNTS VIA MOBEE AND ATM CARDS | Problem: Customer is able to utilize locked amount in T24 through digital channels and ATM thus causing account migration to NPL. | Retail | Subsidiary - Tanzania | Transaction Banking | Nelson Perez | Scrum Leads | Muiruri,Shirleen Kalekye | 2023-04-21 | 2023-08-11 | Miregwa,Carol Moraa | 532 | Active | Business Change or Need | Enterprise and Application | Core Banking | Allocated to Tribe |  |  | 3288 | User Story | C07391 - UTILIZATION OF LOCKED AMOUNTS VIA MOBEE AND ATM CARDS | Gaston Moses. Mchakama <TZA200920@kcbgroup.com> | Blocked | July Sprint A; July Sprint B; July Sprint C
10 | C07399 | Normal Change | 4 - Can Work | Design | KCB BRANCH CCTV TRAFFIC VIA SDWAN PILOT | The goal of this Proof of Concept is to enable the KCB Control room to be able to view live and recorded CCTV footage of KCB Branches via KCB and GLOSEC network. The actualization of the POC is from the theoretical level to practical implementation, and to validate the key concepts. The plan is to interconnect both networks [KCB & GLOSEC] using standard procedures defined by KCB networks team and be able to get only CCTV Traffic from the branches using the best network configuration and performance management. | Technology Infrastructure | KCB - Information Technology | Firewall | Kimathi,Titus Mutuma | Scrum Leads | Otieno, Godfrey Okoth | 2023-04-24 | 2023-10-17 | Minjire, Simon Kibe | 529 | Active | Technology Change or Need | Service request |  |  |  | Service Request | 2664 | User Story | C07399 - KCB BRANCH CCTV TRAFFIC VIA SDWAN PILOT | Benjamin Maina Ndung'u <KEN20838@kcbgroup.com> | Deployment
11 | C07520 | Normal Change | 4 - Can Work | Design | Failed/Delayed ATM transactions Auto-reversals | We are experiencing delays in Auto-reversal of failed ATM transaction. The customer receives an auto-reversal alert via text but the actualization of the reversal takes upto 12 Hours. ITSM Ref: SVC1816182 | ATMs | Shared Services | T24 | Wangombe Patrick K | Scrum Leads | Otieno, Godfrey Okoth | 2023-05-31 | 2023-10-04 | Minjire, Simon Kibe | 492 | Active | Error Correction or Fixes ( RCA required ) | Enterprise and Application | Core Banking | Allocated to Tribe |  | Awaiting resolution | 2813 | User Story | C07520 - Failed/Delayed ATM transactions Auto-reversals | Victor Ochieng Juma <KEN22107-a@kcbgroup.com> | PIR
12 | C07527 | Normal Change | 4 - Can Work | Design | Vooma Recon Tool - Enable authentication on MogoDB | Request to enable authentication or disable mongo DB service attached to the Vooma Recon Tool. This will close an audit item that was flagged as a vulnerability and could be exploited by attackers. A remote attacker can therefore connect to the application database system in order to create, read, update, and delete documents, collections, and databases. | Banking operations | KCB - Information Technology | Corona | Awere Vincent | Scrum Leads | Otieno, Godfrey Okoth | 2023-06-05 | 2023-10-17 | Minjire, Simon Kibe | 487 | Active | Technology Change or Need | Automation and Process Improvement |  | Allocated to Tribe |  |  | 2818 | User Story | C07527 - Vooma Recon Tool - Enable authentication on MogoDB (Mongo DB default credentials) | Elkanah Kibet <KEN16766@kcbgroup.com> | Analysis/Design
13 | C07560 | Normal Change | 4 - Can Work | Design | KCB-KENYA F5 LOAD BALANCER REFRESH PROJECT | This references a new project for KCB Kenya F5 load balancers that will be replacing Radware LB and existing old F5 hardware that resides on Vooma environment. | Technology Infrastructure | KCB - Information Technology | Switches | Kimathi,Titus Mutuma | Scrum Leads | Otieno, Godfrey Okoth | 2023-06-13 | 2023-10-18 | Minjire, Simon Kibe | 479 | Active | Project | Clean Up |  | Clean Up Validation |  |  | 2881 | User Story | C07560: KCB-KENYA F5 LOAD BALANCER REFRESH PROJECT | Peninah Wanjiku Nganga <KEN22106@kcbgroup.com> | Deployment
14 | C07643 | Normal Change | 4 - Can Work | Design | ATM AUDIT RESOLUTION IMPLEMENTATION | ATM/CDM security system Audit resolution implementation. | Technology Infrastructure | KCB - Information Technology | Active Directory | Gakuya, Peter Wilson Githinji | Scrum Leads | Otieno, Godfrey Okoth | 2023-07-05 | 2023-10-18 | Minjire, Simon Kibe | 457 | Active | Technology Change or Need | Clean Up |  | Delivered | Delivered |  | 3030 | User Story | C07643 - ATM AUDIT RESOLUTION IMPLEMENTATION - NAME CHANGE | Juma, Victor Ochieng <KEN22107@kcbgroup.com> | Closed
15 | C07705 | Normal Change | 4 - Can Work | Design | IMPLEMENTATION OF PHASE 2 ON CHATBOT - FINANCIAL SERVICES | This is to kickstart implementation of financial services on the chatbot as per attached SRS | Operations | Subsidiary - Uganda | all channels | Daphine Gumoshabe | Scrum Leads | Matengo, Davis Obonyo Ochieng | 2023-07-21 | 2023-10-13 | Okodo, James | 441 | Active | 0 | Clean Up |  | Delivered | Delivered | Valid In progress | 4212 | User Story | C07705: PHASE 2 OF CHATBOT-AUTHENTICATED SERVICES | Daizy Berucan <UGA32347@kcbgroup.com> | Pilot
16 | C07748 | Normal Change | 4 - Can Work | Design | UPLOAD OF CUSTOMER EXCELLENCE QUALITY ASSURANCE TEMPLATES ON SHAREPOINT | Colleagues, Kindly assist to upload the reviewed QA templates on share point. Find below attachments Below is the email communication shared with IT team From: Okodo, James <JOkodo@kcbgroup.com> Sent: Friday, August 4, 2023 4:37 PM To: Gedion Mwangi Macharia <gmmacharia@kcbgroup.com> Cc: Caleb Kagera <ckagera@kcbgroup.com>; Francis Achollah <fachollah@kcbgroup.com>; Diana Chepkurui Cheruiyot <dcchepkurui@kcbgroup.com> Subject: RE: Upload of Revised QA Templates on Sharepoint Hello Gedion, Please raise a change for this on ITSM to enable us effective support delivery as discussed. Kind regards, Onyango Okodo IT Relationship Management Mobile: +254723788435 KCB Head Office, Kencom House, 7th Floor P. O. Box 48400-00100 From: Gedion Mwangi Macharia <gmmacharia@kcbgroup.com> Sent: Wednesday, August 2, 2023 11:54 AM To: Okodo, James <JOkodo@kcbgroup.com> Cc: Caleb Kagera <ckagera@kcbgroup.com>; Francis Achollah <fachollah@kcbgroup.com>; Diana Chepkurui Cheruiyot <dcchepkurui@kcbgroup.com> Subject: RE: Upload of Revised QA Templates on Sharepoint Dear James, As you upload the new templates, please ensure the previous QA scores/checks and any other related data can be stored somewhere we can access it. Kind Regards, Gedion Mwangi Macharia Customer Excellence Standards KCB Customer Excellence KCB Head Office, Kencom House, 4th Floor P. O. Box 48400-00100 Nairobi CISCO: 13125 www.kcbbankgroup.com CALL: 0711 087000 or 0732 187000 EMAIL: gmmacharia@kcbgroup.com SMS 22522 From: Diana Chepkurui Cheruiyot <dcchepkurui@kcbgroup.com> Sent: Wednesday, August 2, 2023 10:33 AM To: Okodo, James <JOkodo@kcbgroup.com> Cc: Caleb Kagera <ckagera@kcbgroup.com>; Gedion Mwangi Macharia <gmmacharia@kcbgroup.com>; Francis Achollah <fachollah@kcbgroup.com> Subject: RE: Upload of Revised QA Templates on Sharepoint ++@Okodo, James kindly support. Best Regards, Diana Cheruiyot From: Francis Achollah Sent: Wednesday, August 2, 2023 10:15 AM To: Diana Chepkurui Cheruiyot <dcchepkurui@kcbgroup.com> Cc: Caleb Kagera <ckagera@kcbgroup.com>; Gedion Mwangi Macharia <gmmacharia@kcbgroup.com> Subject: RE: Upload of Revised QA Templates on Sharepoint @Diana Chepkurui Cheruiyot, FYA Regards, Achollah. From: Gedion Mwangi Macharia <gmmacharia@kcbgroup.com> Sent: Wednesday, August 2, 2023 10:11 AM To: Francis Achollah <fachollah@kcbgroup.com> Cc: Caleb Kagera <ckagera@kcbgroup.com> Subject: Upload of Revised QA Templates on Sharepoint Dear Francis, Please assist to upload the attached revised QA templates for branch (data capture & case handling) and Head office units (Case handling) on the share point. Below are the link for accessing the shared folder. BRANCH EVALUATION-CASE HANDLING - New Item HQ QA Evaluation Case - New Item Branch Data Capture - New Item Kind Regards, Gedion Mwangi Macharia Customer Excellence Standards KCB Customer Excellence KCB Head Office, Kencom House, 4th Floor P. O. Box 48400-00100 Nairobi CISCO: 13125 www.kcbbankgroup.com CALL: 0711 087000 or 0732 187000 EMAIL: gmmacharia@kcbgroup.com SMS 22522 | Customer Experience | KCB - Customer Experience | all channels | Gedion Mwangi Macharia | Scrum Leads | Otieno, Godfrey Okoth | 2023-08-04 | 2023-10-17 | Okodo, James | 427 | Active | 0 | Channels and Cards |  | Allocated to Tribe |  |  | 3505 | User Story | C07748 - UPLOAD OF CUSTOMER EXCELLENCE QUALITY ASSURANCE TEMPLATES ON SHAREPOINT | Huxley Magak <KEN22936@kcbgroup.com> | UAT | August A; July Sprint A; July Sprint B; July Sprint C; September Sprint A
17 | C07811 | Normal Change | 4 - Can Work | Design | Instana Agent Installation | Installation of Instana monitoring tool agent in technology hosts for application performance and infrastructure monitoring. | IT-Monitoring | KCB - Information Technology | Instana | Marami, Edna Marura | Scrum Leads | Otieno, Godfrey Okoth | 2023-08-18 | 2023-10-18 | Minjire, Simon Kibe | 413 | Active | Technology Change or Need | Clean Up |  | Delivered | Delivered |  | 4791 | User Story | C07811-Instana Implementation | Huxley Magak <KEN22936@kcbgroup.com> | Deployment
18 | C07818 | Normal Change | 4 - Can Work | Design | MULTIPLE TRANSACTION ALERTS IBANK B2C | The system has been sending multiple alerts in some instances for the same Ibank B2C transaction. From our analysis, this happens when Interswitch receives multiple callbacks from Vooma ESB for the same transaction, each duplicate callback triggers an SMS for the same transaction. The duplicate callbacks are received by ESB from Safaricom. The agreed solution is for Interswitch to check the SMSMESSAGES table for an entry with the same reference number. If record exists, ignore SMS logging otherwise log a new SMS Notification. | I.T Digital Channels | KCB - Information Technology | Biller Engine across all companies | Kasanga, Judith Nthenya | Scrum Leads | Gitau, Kevin | 2023-08-21 | 2023-10-18 | Minjire, Simon Kibe | 410 | Active | Error Correction or Fixes ( RCA required ) | Channels and Cards |  | Allocated to Tribe |  |  | 3328 | User Story | C07818 - MULTIPLE TRANSACTION ALERTS IBANK B2C | Huxley Magak <KEN22936@kcbgroup.com> | Deployment
19 | C07845 | Normal Change | 4 - Can Work | Design | INCORPORATION OF ADDITIONAL FIELDS ON CQ FOR REPORT SHARING PURPOSES | Legal Securities oversees perfection of security documents for the Bank with the assistance of external advocates. With this role, the business requires that we share with them monthly reports on the outstanding applications and the reasons for non-closure. We have been compiling a report on excel format as attached but due to the increase in the number of applications, we are unable to keep on updating the excel and the status option of the CQ. Our request is to have additional fields incorporated in CQ to enable us access reports directly from CQ using the status updates and the registries where the security are being registered. | Securities and Documentation Centre | KCB - Company Secretary | Credit Quest | Kiongo, Rachel Wambui | Scrum Leads | Matengo, Davis Obonyo Ochieng | 2023-09-05 | 2023-10-17 | Okodo, James | 395 | Active | Business Change or Need | Lending |  | Allocated to Tribe |  |  | 3392 | User Story | C07845 - INCORPORATION OF ADDITIONAL FIELDS ON CQ FOR REPORT SHARING PURPOSES | Caroline Kathaaara <ken10904@kcbgroup.com> | Blocked
20 | C08116 | Normal Change | 4 - Can Work | Validation | IMPLEMENTATION OF APPROVAL LIMITS IN INTERSWITCH SYSTEM FOR DFS OPS,CARD OPS AND CPC | The current set up of Interswitch system does not have approval limits set the same way it is in T24.All posted transactions can be approved by any approver irregardless of the amounts. Kindly implement approval limits as set in T24 in Interswitch to minimize risk of financial loss.Sample user set up in T24 attached for DFS OPS. http://172.16.103.138/interswitch/#/approval | DFS-Operation | Shared Services | T24 | Chaiko, Christopher | Demand Management | 0 | 2023-11-22 | 2023-12-06 | Miregwa,Carol Moraa | 317 | Active | Other Operational Changes and maintenance | Enterprise and Application | Core Banking | Allocated to Tribe |  |  | 4900 | User Story | C08116 - IMPLEMENTATION OF APPROVAL LIMITS IN INTERSWITCH SYSTEM FOR DFS OPS,CARD OPS AND CPC | Onyango, Suzan Achieng <KEN22988@kcbgroup.com> | New | Enhancement; Sybrin; T24
21 | C08139 | Normal Change | 4 - Can Work | Design | KCB MENTORSHIP APP | HR runs employee capacity building programs and one of the ways is through mentorship. We would like to create an app where we can have our programs e.g currently the Women in Leadership together with other future programs , where we have a depository to store all documents/information with respect to the program, communicate with the group members, data analytics, notifications, e-learnings etc. We would also like a mentors space, mentee space, coordinators space created etc. We would like this app to have capacity to accommodate other mentorship programs that may arise. | Learning Development & Talent | Human Resource | Power Apps | Gakii Makena Mugambi | PMO | Mwihia, Alice | 2023-12-01 | 2023-12-11 | Ishmael Gwama Mvurya | 308 | Active | Business Change or Need | Automation and Process Improvement |  | Allocated to Tribe |  |  | 3754 | User Story | C08139 - KCB MENTORSHIP APP | Benjamin Maina Ndung'u <KEN20838@kcbgroup.com> | CAB Review
22 | C08282 | Normal Change | 4 - Can Work | Design | SOPRA DATAFEEDS SPOOLING FROM THE STANDBY DB | Sopra PostEod which is basically generation of reports has been doing upwards of 4 hours during the EOD process. This change intends to have the report fetched directly from the db using the existing Sopra db link from edwh. The balance data query has been shared with edwh team for a start to confirm if it can work. | I.T Digital Channels - Fintech | KCB - Information Technology | Data Warehouse | Dismas Kipkoech Solary | Scrum Leads | Elkanah Kibet | 2024-02-08 | 2024-02-12 | Okodo, James | 239 | Active | Business Change or Need | Enterprise and Application | Core Banking | Allocated to Tribe |  |  | 4013 | User Story | C08282 - SOPRA DATAFEEDS SPOOLING FROM THE STANDBY DB | Caroline Kathaaara <ken10904@kcbgroup.com> | UAT | July Sprint B; July Sprint C
23 | C08381 | Normal Change | 4 - Can Work | Validation | Oracle Fusion(HR) Intergration to Active Directory | Integration between Oracle Fusion (Oracle Recruiting Cloud) with Active Directory | HR-Shared Service Department | KCB - Human Resources | ORACLE HR | Japhet Kibet Cheboiywo | Demand Management | Grace Wambui Kiguru | 2024-03-01 | 2024-03-06 | Grace Wambui Kiguru | 217 | Active | Business Change or Need | Enterprise and Application | Application | Allocated to Tribe |  | Change delivered and | 4084 | User Story | C08381 - Oracle Fusion(HR) Intergration to Active Directory | Carol Moraa Miregwa <KEN21302@kcbgroup.com> | Deployment
24 | C08403 | Normal Change | 4 - Can Work | Design | KCBSS ATMs Surcharge of 2.5%, MinUSD10 for Non-KCB Issued Cards. | Problem Statement Description: A review of transactions undertaken by international clients on our ATMs indicate that KCB Bank South Sudan is not receiving the full settlement amount that is inclusive of the applicable tariff. All the settlement undertaken since the ATMs were operationalized have only been on withdrawn amount while applicable tariff of 2.5% min USD10 fee has not been provided as part of the settlement. An issue to be taken up separately with the relevant parties. In the meantime, we would like to make changes to enable KCBSS ATMs support surcharging of international customers who transact on KCB South Sudan ATMs. This covers cards not issued by KCB or any of its subsidiaries. There are many transactions of non-KCB issued Cards transacting on our terminals with zero commissions. Proposed Solution We would like to achieve the following; 1. Provide an onscreen menu for such transactions showing that the customer will be charged 2.5%, minimum USD10 of the withdrawal amount for each transaction undertaken. 2. Apply the 2.5%, Min USD10 charge on any customer if using an international card i.e., Cards that are not issued by KCB Bank. Below are sample transactions; Sample Transactions: 1.FT23349FK29B - 4659 4*** **** 8433 - HSBC BANK PLC - Charge waived. 2. FT23346YSVK2 - 4840 7*** **** 1292 – ECO BANK SS - Charge Waived. Effect of not implementing: Loss of income line from our ATMs and eventual decline in economic value. | IT | Subsidiary - South Sudan | all channels | Njiru, John | PMO | Kibe, Marion | 2024-03-05 | 2024-03-14 | Ishmael Gwama Mvurya | 213 | Active | 0 | Channels and Cards |  | Allocated to Tribe |  | The change has not been assigned a tribe. The Business case is available | 12671 | User Story | C08403 - KCBSS ATMs Surcharge of 2.5% MinUSD10 for Non-KCB Issued Cards. | Onyango, Suzan Achieng <KEN22988@kcbgroup.com> | Analysis/Design
25 | C08404 | Standard Change | 4 - Can Work | Validation | Cheques Bridge Restriction Issue | Cheque transactions were failing with error “Debit Account Category Posting Not Allowed!...Rejecting..”. On checking the bnk_channel$restrict_accounts table, there was no restriction done for cheque channel. The restrictions done were for other channels but affected the cheques bridge which rejected transaction based only that the account is configured in the bnk_channel$restrict_accounts table without factoring in the channel. Below is a log extract of the error. 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1306 - 24060KAHP¦ Exclusive Lock Acquired For [010973012411106779630] ? : true 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1337 - 24060KAHP¦172.20.22.40¦ Balance Before Transaction(102): 52407.90 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1350 - 24060KAHP¦172.20.22.40¦ Balance Before Transaction(103): 86438051.54 2024-02-29 12:32:15 INFO AccountGCRetrictionCheck:39 - TX: Account [1305402235] is restricted by GROUP_CONDITION[11104] Channel[CHEQUES$CHANNEL]: [false] 2024-02-29 12:32:15 INFO AccountGCRetrictionCheck:67 - TX: ACCOUNT IS RESTRICTED 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1527 - 24060KAHP: Debit Account Category Posting Not Allowed!...Rejecting.. 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1556 - 24060KAHP¦172.20.22.40¦ In Posting Restrict 103!! Type Credit Restrict On Dr Account 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1559 - 24060KAHP¦172.20.22.40¦ Posting Restrict102: Posting Restrict103:RESTRICTED 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1560 - 24060KAHP¦172.20.22.40¦ inactiveaccount102: inactiveaccount103: 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1561 - 24060KAHP¦172.20.22.40¦ daocheck103: 4143,Category103: [1002], daocheck102:4143, SubSeg102: [7103] 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1562 - 24060KAHP¦172.20.22.40¦ RESTR_INPUT_BY103: 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1630 - 24060KAHP¦172.20.22.40¦ Balance After Transaction(103): 86438051.54 2024-02-29 12:32:15 INFO OfflineChequesFormatter:1834 - 24060KAHP¦172.20.22.40¦ Balance After Transaction(102): 52407.90 2024-02-29 12:32:15 INFO OfflineChequesFormatter:2129 - 24060KAHP¦172.20.22.40¦ InMessage: null 2024-02-29 12:32:15 INFO OfflineChequesFormatter:2165 - 24060KAHP¦172.20.22.40¦ validateMessageOut: Type Credit Restrict On Dr Account 2024-02-29 12:32:15 INFO OfflineChequesFormatter:2292 - replymappingout 40142330072511547 Attached is the email trail of the issue. | I.T Digital Channels | KCB - Information Technology | ESB Bridge | Wanjohi, Peter Kabira | Demand Management | 0 | 2024-03-06 | 2024-03-08 | alert | 212 | Active | 0 | Enterprise and Application | Application | Allocated to Tribe |  |  | 4083 | User Story | C08404 - Cheques Bridge Restriction Issue | Benjamin Maina Ndung'u <KEN20838@kcbgroup.com> | UAT | August A; July Sprint B; July Sprint C
26 | C08620 | Normal Change | 4 - Can Work | Validation | Encryption of credit cards statements before sending to customers. | Kindly initiate encryption of credit cards statements before sending to customers. | Card Business | KCB - Retail Banking | Tranzware | Kenneth Wamiti Kirathe | Demand Management | 0 | 2024-05-07 | 2024-05-15 | alert | 150 | Active | Business Change or Need | Channels, CDM, ATM, IMT and Diaspora |  | Allocated to Tribe |  |  | 8928 | User Story | C08620 - Encryption of credit cards statements before sending to customers. | Onyango, Suzan Achieng <KEN22988@kcbgroup.com> | Analysis/Design
27 | C08673 | Standard Change | 4 - Can Work | Validation | To resolve pesalink transaction query marking failed transactions as successful". | Kindly reinstate the auto reversal of merchant payment entries from PESALINK SUSPENSE ACC KES1400541530001 back to Merchant Payments EFT A/C–KES1401191530001 which has not been happening since 1.12.2023.This has been causing a debit difference to run in the Pesalink suspense account. This is as a result of failed pesalink transactions being marked as successful upon status query. | Card Operations Department | Shared Services | Biller Engine | Peter, Jacquelynn Nduku | Demand Management | 0 | 2024-05-20 | 2024-06-11 | alert | 137 | Active | 0 | Channels and Cards |  | Allocated to Tribe |  |  | 7175 | User Story | C08673 - To resolve pesalink transaction query marking failed transactions as successful | Joseph Gitonga Njeru <KEN16849@kcbgroup.com> | Development
28 | C08689 | Standard Change | 4 - Can Work | Validation | Interswitch PGP files entries for Mpesa Holding account | There are strange FT entries in the Mpesa Holding acccount files sent to interswitch that are missing in T24. We need to incorporate IP Address logging to identify the source of these transactions. | Banking operations | KCB - Information Technology | Integrated POS | Murugami, Anthony | Demand Management | 0 | 2024-05-22 | 2024-06-11 | alert | 135 | Active | Error Correction or Fixes ( RCA required ) | Incident |  | Allocated to Tribe |  |  | 4827 | User Story | C08689 - Interswitch PGP files entries for Mpesa Holding account | Rahab Wambuku Mwenda <KEN19991@kcbgroup.com> | Deployment
29 | C08696 | Normal Change | 4 - Can Work | Logging | Expanding 'Lipa Na KCB' Services to Tanzania by Integrating TANQR Standards | The integration of the Tanzania Quick Response (TANQR) standard and Tanzania Instant Payment System (TIPS) presents an exceptional opportunity for KCB Tanzania (KCB TZ) to broaden its merchant services. By adopting the TANQR standards for creating Merchant IDs and QR codes, KCB TZ aims to enhance the efficiency of onboarding merchants. This strategic move will enable merchants to accept payments from a diverse customer base across multiple Financial Service Providers (FSPs). With standardized QR codes and Merchant IDs, KCB TZ merchants can receive payments seamlessly from customers of various FSPs, enhancing transaction convenience and security. The TANQR standard, issued by the Bank of Tanzania, sets a framework for a unified QR code payment system across the nation. It is rooted in the EMVCo QR Code Specification for Payment Systems, specifically the Merchant-Presented Mode, and is designed to support several crucial objectives: Interoperability: Ensures compatibility across different payment service providers, facilitating smooth QR code transactions across diverse platforms and financial institutions. Security: Enhances security measures to protect against fraud and unauthorized transactions, prescribing specific security protocols and data management practices. Electronic Payments: Promotes the adoption of electronic payments to boost financial inclusion and decrease reliance on cash within the Tanzanian market. Regulation and Oversight: Maintained under the regulatory purview of the Bank of Tanzania, which monitors compliance and implementation, thus addressing potential risks associated with QR code-based transactions. The TANQR standard meticulously outlines the data structure for QR codes, which includes merchant information, transaction details, and other essential elements needed for processing payments. It differentiates between static QR codes, used for multiple transactions, and dynamic QR codes, tailored for individual transactions. Furthermore, the standard provides detailed guidelines for the format and content of QR codes. This includes specifications for merchant account information, additional merchant details, transaction values, and other optional data fields. This structured approach ensures a consistent and reliable payment process, thus improving the user experience and fostering the growth of digital transactions in Tanzania. By integrating TANQR standards, KCB TZ not only adheres to national payment regulations but also leverages cutting-edge technology to provide superior service offerings, ultimately enhancing merchant satisfaction and consumer engagement. | Retail | Subsidiary - Tanzania | Biller Engine | Nelson Perez | Change Management | 0 | 2024-05-23 | 2024-05-23 | linker | 134 | Active | Business Change or Need | Channels, CDM, ATM, IMT and Diaspora |  | Allocated to Tribe |  | Open and Valid | 4828 | User Story | C08696 - Expanding 'Lipa Na KCB' Services to Tanzania by Integrating TANQR Standards | Joseph Gitonga Njeru <KEN16849@kcbgroup.com> | Development | Tanzania
30 | C08699 | Normal Change | 4 - Can Work | Design | ABC PHASE 3 | ABC PHASE 3 ON CARDED WITHDRAWALS, MINI STATEMENT AND BALANCE INQUIRY | Retail | Subsidiary - Uganda | Agency Banking | Andrew Akatukunda | Scrum Leads | Otieno, Godfrey Okoth | 2024-05-23 | 2024-07-03 | Okodo, James | 134 | Active | Business Change or Need | Channels and Cards |  | Allocated to Tribe |  |  | 5700 | User Story | C08699-ABC PHASE 3 | Joseph Gitonga Njeru <KEN16849@kcbgroup.com> | SIT | September Sprint A
31 | C08766 | Normal Change | 4 - Can Work | Design | PESALINK Default Sender Name for KCB outgoing Payments | Amend Sender Name to read Customers name for Pesalink Transactions. Some KCB payments are being sent with a default sender name, causing the beneficiaries difficulty in reconciling these payments as the sender name appears as "KCB BANK". | Digital Financial Services | KCB - Digital Financial Services | all channels | Roxa C. Ngeno | Scrum Leads | Otieno, Godfrey Okoth | 2024-06-03 | 2024-07-03 | Okodo, James | 123 | Active | 0 | Channels and Cards |  | Allocated to Tribe |  |  | 5564 | User Story | C08766 - PESALINK Default Sender Name for KCB outgoing Payments | Charles Kiplangat <KEN10271@kcbgroup.com> | Blocked | July Sprint A; July Sprint B; July Sprint C; September Sprint B
32 | C08801 | Normal Change | 4 - Can Work | Validation | ITSM SMAX upgrade | In the year 2016, Technology embarked on a journey to fundamentally transform its capabilities, with I.T Service Management being a core component of the transformation, to ensure its services meet the requirements of customers. Central to the success of this was the implementation of the HP IT service Management Tool that primarily aimed at transforming Technology Service Management capabilities. The IT service Management tool focused on delivering an enterprise ITSM technology solution, while accelerating the evolution of existing and development of new ITIL-based processes. The tool would also assist in driving enterprise adoption of new ITIL processes. | Client Support | Technology | ITSM | Catherine Mwikali Nguyo | Demand Management | 0 | 2024-06-13 | 2024-07-01 | alert | 113 | Active | Other | Technology Refresh & Evolution - Platforms |  | Allocated to Tribe |  |  | 5612 | User Story | C08801 - ITSM SMAX upgrade | Edwin Okumu <KEN207712@kcbgroup.com> | SIT
33 | C08877 | Normal Change | 4 - Can Work | Design | REQUEST TO UPGRADE API SECURITY IFO AIRTEL ESCROW | Airtel API access requires manual password change on a monthly basis and this done with dependency on the Airtel security Team. Airtel has now upgraded the security of the API access to allow for self-service on the password change for the API | Corporate Banking | Subsidiary - Uganda | all channels | Lydia Monday Mangeni | Scrum Leads | Wakagwi, Maureen | 2024-07-11 | 2024-07-24 | Okodo, James | 85 | Active | 0 | Integrations |  | Allocated to Tribe |  | Not for Partnerships and Open APIs, Evaluate and re-assign | 6535 | User Story | C08877 - REQUEST TO UPGRADE API SECURITY IFO AIRTEL ESCROW | Caroline Kathaaara <ken10904@kcbgroup.com> | New
34 | C08924 | Normal Change | 4 - Can Work | Design | Upgrade of Canon Print Server Application | We wish to upgrade the uniflow application on all 5 print servers. | I.T Business Productivity | KCB - Information Technology | print server | Bethwel Kipruto Cheres | Transition Management | Mbala, Gardy Orega | 2024-07-25 | 2024-08-07 | Ishmael Gwama Mvurya | 71 | Active | Other Operational Changes and maintenance | Technology Refresh & Evolution - Platforms |  | Allocated to Tribe |  |  | 12670 | User Story | C08924 - Upgrade of Canon Print Server Application | Onyango, Suzan Achieng <KEN22988@kcbgroup.com> | Analysis/Design
35 | C08966 | Normal Change | 4 - Can Work | Design | KCB Account to Account Transfer - Error on Account Name Validation Service | Errors had previously been noted on the account "Hakikisha" service while sending account details request to T24. Investigations revealed that the endpoint which is load balanced on F5 was noted to be unresponsive. Checks on the F5 service were done and it was noted that there was a configuration mismatch expected to have emanated from migration from old F5 to the new F5. Upon further analysis, it was noted that the responses were not getting to Vooma as they had different tags (a different namespace ns2) compared to those that were successful (ns3). OCP is unable to consume any response with ns2. A solution for this has problem has been developed by the BSS team., and we seek approval to proceed to testing and subsequent deployment. | Digital Financial Services | KCB - Digital Financial Services | all channels | Martin Musyimi Peter | Scrum Leads | Otieno, Godfrey Okoth | 2024-08-02 | 2024-08-07 | Ishmael Gwama Mvurya | 63 | Active | 0 | Channels and Cards |  | Allocated to Tribe |  |  | 7176 | User Story | C08966 - KCB Account to Account Transfer - Error on Account Name Validation Service | Benjamin Maina Ndung'u <KEN20838@kcbgroup.com> | UAT
36 | C08970 | Normal Change | 4 - Can Work | Design | Moving Blueriver Corporate CDMs to KCB Centralized server | KCB currently operates 8 Cash Deposit Machines that run on the Blue River system, which is external to the KCB server. At present, logs from CDM machines are only accessible through physical retrieval at the CDM locations. We have initiated discussions with the vendor to transition these CDMs to the KCB server, enabling central monitoring and enhanced data privacy and security. Your assistance in implementing this change would be greatly appreciated. | Cash Management | KCB - Corporate Banking | T24 | Wandera, Richard | Scrum Leads | Omulo, Laurette | 2024-08-05 | 2024-08-07 | Ishmael Gwama Mvurya | 60 | Active | Business Change or Need | Channels, CDM, ATM, IMT and Diaspora |  | Allocated to Tribe |  |  | 6981 | User Story | C08970 - Moving Blueriver Corporate CDMs to KCB Centralized server | Caroline Kathaaara <ken10904@kcbgroup.com> | Blocked
37 | C09023 | Normal Change | 4 - Can Work | Design | NESSUS AGENTS INSTALLATION | We GCS intend to install Nessus agents on ATM and CDMs in Kenya in a phased approach. This is in line with Group Enterprise architecture vulnerabilities management standard. | Tech security | KCB - Information Technology | Server | Denzel Ndegwa | Scrum Leads | Omulo, Laurette | 2024-08-13 | 2024-08-20 | Ishmael Gwama Mvurya | 52 | Active | Technology Change or Need | Channels, CDM, ATM, IMT and Diaspora |  | Allocated to Tribe |  |  | 8778 | User Story | C09023 - NESSUS AGENTS INSTALLATION | Denzel Ndegwa <KEN20438@kcbgroup.com> | Analysis/Design
38 | C09036 | Normal Change | 4 - Can Work | Design | Closure of audit issues identified in the KCB Mobile Banking App in Tanzania | This is request seeks to close two security issues identified during an audit of the KCB Mobile Banking App in Tanzania. The envisaged fix will: 1.) Ensure that mobile application responses do not expose sensitive information such as account number or account name. If any of this information needs to be included in the response, then the said response should be encrypted to prevent disclosure – at the moment, the encryption has only been done on the requests and not responses hence there is disclosure of information. 2) Enforce Application Programming Interface (API) rate limiting on KCB Mobile application, which will limit the number of API requests a user can make within a certain period - currently, encryption has implemented done on the requests, making it difficult for attackers to perform iteration. However, rate limiting controls have not been implemented. Since the same mobile app code base is used in multiple countries, the audit issues picked up in Tanzania are also potentially present in Kenya, South Sudan and Burundi hence there is need to have a holistic solution in place. | Digital Financial Services | KCB - Digital Financial Services | all channels | Martin Musyimi Peter | Scrum Leads | Wakagwi, Maureen | 2024-08-14 | 2024-08-20 | Ishmael Gwama Mvurya | 51 | Active | 0 | Integrations |  | Allocated to Tribe |  |  | 8245 | User Story | C09036 - CLOSURE OF AUDIT ISSUES IDENTIFIED IN THE KCB MOBILE BANKING APP KCBTZ | Caroline Kathaaara <ken10904@kcbgroup.com> | New
39 | C09042 | Normal Change | 4 - Can Work | Design | commission settlement task failure Fix | The commission settlement task failed to be executed in June 2023. Since then, the commission settlement task fails due to discontinuous settlement. As a result, the commission cannot be rolled up normally. In this case, the settlement record needs to be supplemented in the previous cycle and then rolled up and delivered. we have some agent/merchant commissions that were never settled from last year 2023. | 0 | 0 | Vooma SP | Idah Karendi Njoka | Scrum Leads | Otieno, Godfrey Okoth | 2024-08-15 | 2024-08-20 | Ishmael Gwama Mvurya | 50 | Active | Error Correction | Channels and Cards |  | Allocated to Tribe |  |  | 8781 | User Story | C09042 - Commission settlement task failure Fix | Michael, Chesseto Tung <KEN23301@kcbgroup.com> | Analysis/Design
40 | C09043 | Normal Change | 4 - Can Work | Design | Request to redesign KCB APP enquiry services - Daraja to KNOBS | The request is to redesign the ocp services kcb-mobi-get-accountbalance and kcb-mobi-get-account-details to call KNOBS instead of daraja . The change will address KCB APP Downtime as captured in RCA IM124876 and IM124899 | I.T Digital Channels | KCB - Information Technology | NOBS(OFFLINE_ SERVICE) | Nelson Mutangili Muia | Scrum Leads | Wakagwi, Maureen | 2024-08-15 | 2024-08-20 | Ishmael Gwama Mvurya | 50 | Active | Error Correction or Fixes ( RCA required ) | Integrations |  | Allocated to Tribe |  |  | 9839 | User Story | C09043 - Request to redesign KCB APP enquiry services - Daraja to KNOBS | Arthur Joseph Kinyanjui <KEN21811@kcbgroup.com> | SIT
41 | C08973 | Standard Change | 4 - Can Work | Validation | Tranzware Online (TWO) RHEL Upgrade to 8.8 | Tranzware Online (TWO) Upgrade of RHEL from 7.9 to 8.8 | I.T Digital Channels | KCB - Information Technology | Server Upgrade | Mungai, Allan Njuguna | Demand Management | 0 | 2024-08-05 | 2024-08-27 | alert | 60 | Active | 0 | Channels and Cards |  | Allocated to Tribe |  |  | 6975 | User Story | C08973 - Tranzware Online (TWO) RHEL Upgrade to 8.8 | Victor Ochieng Juma <KEN22107-a@kcbgroup.com> | PIR
42 | C07676 | Normal Change | 4 - Can Work | Design | EQMS END TO END CUSTOMER JOURNEY FOR BRANCH NON CASH TRANSACTIONS | Integration between EQMS and CQ for loan applications and BPM for account opening. This is to track customer journey after EQMS ticket is closed and requests are captured on CQ and BPM | I.T Business Productivity | KCB - Information Technology | EQMS | Mutai, Richard Kipkoech | Scrum Leads | Otieno, Godfrey Okoth | 2023-07-17 | 2023-10-18 | Minjire, Simon Kibe | 445 | Active | Business Change or Need | Channels and Cards |  | Allocated to Tribe |  |  | 3113 | User Story | C07676 - EQMS END TO END CUSTOMER JOURNEY FOR BRANCH NON CASH TRANSACTIONS | Hillary Ogeto Oseko <KEN22965@kcbgroup.com> | Closed
43 | C09166 | Normal Change | 4 - Can Work | Design | Pesalink Auto Reversal Service | We need a way of auto-reversing Failed Pesalink transactions instead of waiting for reconciliation so that customers are able to access funds and re-do the transaction after amending the needful eg Erroneous Beneficiary account, Crosscurrency transaction etc. | I.T Digital Channels - Fintech | KCB - Information Technology | Biller Engine | Njuguna, Catherine | Scrum Leads | Otieno, Godfrey Okoth | 2024-09-11 | 2024-09-17 | Ishmael Gwama Mvurya | 23 | Active | Other Operational Changes and maintenance | Channels and Cards |  | Allocated to Tribe |  |  | 11989 | User Story | C09166 - Pesalink Auto Reversal Service | Caroline Kathaaara <ken10904@kcbgroup.com> | New
44 | C09174 | Normal Change | 4 - Can Work | Design | Subject: Implementation of deposits fees wave and 1% Tax collection on Agent deposits done through Mobi Bridge - This is a follow up to the partial implementation of C07881 and C08608. | Dear Team, Please assist to resolve transactions processed on Mobi bridge that hinder full implementation of change C07881 (Apply 1% Tax fee/Charge on each commission earned by a KCB Burundi agent) and C08608 ( Agency Fee Discrepancy ) The first change intended to collect a tax on revenue earning transaction (deposit and withdrawal) carried out by agents and remunerated by the bank. The leg of agency transaction carried out on agency bridge were successfully implemented but the transactions going through mobi bridge were not implemented hence consequently 1% tax not collected as well The latter change C08608 was partially implemented where agency deposits through agency bridge were implemented but agency deposits through mobi bridge were not implemented hence consequently 1% tax not collected as well | Channels | Subsidiary - Burundi | Agency Banking | Joseph Michel Vyankamvuga | Scrum Leads | Matengo, Davis Obonyo | 2024-09-12 | 2024-09-17 | Ishmael Gwama Mvurya | 22 | Active | Regulatory requirement (Regulatory notice or approval from O | Enterprise and Application | Application | Allocated to Tribe |  |  | 11249 | User Story | C09174 - Implementation of deposits fees wave and 1% Tax collection on Agent deposits done through Mobi Bridge | Simon Mandi Mutua <KEN15890@kcbgroup.com> | Development
45 | C09178 | Normal Change | 4 - Can Work | Validation | Vooma and Sopra Environment Storage Migration To Dorado 18000 | The change involves migrating storage from the current Oceanstor 5500 V3 and Oceanstor 6800 V3 storages, which are out of support and nolonger supported by the vendor, To Oceanstor Dorado 18000 V6. | 0 | 0 | Vooma | Dennis Njenga Wanjiku | Demand Management | 0 | 2024-09-16 | 2024-09-24 | alert | 18 | Active | Other | Technology Refresh & Evolution - Platforms |  | Allocated to Tribe |  |  | 11373 | User Story | C09178 - Vooma and Sopra Environment Storage Migration To Dorado 18000 | Grace Wambui Kiguru <KEN20805@kcbgroup.com> | Deployment
46 | C09182 | Normal Change | 4 - Can Work | Design | Erroneous Insufficient Funds | This error is on Daraja The Conversion logic for Cross currency transactions involving two FCY is erroneous. Therefore customer gets an error when funds are sufficient eg a customer transferring 8432 CAD its converting to USD 11154.08 making his account of OnlineWorkingBalance USD 8596.15 seem insufficient when the right conversion should have brought the figure to the neighbourhood of 6000 USD Please look into Daraja and amend. Catherine | I.T Digital Channels - Fintech | KCB - Information Technology | Internet Banking System | Njuguna, Catherine | Scrum Leads | Mutinda, Benjamin Nzioki - Technology | 2024-09-17 | 2024-09-26 | alert | 17 | Active | Error Correction or Fixes ( RCA required ) | Integrations |  | Allocated to Tribe |  |  | 11991 | User Story | C09182 - Erroneous Insufficient Funds | Sakawa Elijah Bob <KEN19323@kcbgroup.com> | New
47 | C09185 | Normal Change | 4 - Can Work | Design | SWIPE X MISSING TRANSACTIONS | The change is to resolve issues where transactions are successful on swipe x while they do not appear on estatement. | Card Business | KCB - Retail Banking | Agency Banking | Karugu, Harun | Scrum Leads | Otieno, Godfrey Okoth | 2024-09-18 | 2024-09-26 | Okodo, James | 16 | Active | Business Change or Need | Channels and Cards |  | Allocated to Tribe |  |  | 13675 | User Story | C09185 - SWIPE X MISSING TRANSACTIONS | Musembi, Brian Mutisya <KEN22941@kcbgroup.com> | Analysis/Design
48 | C09189 | Normal Change | 4 - Can Work | Design | Interswitch Failing Upload of transactions & remove locks | Interswitch is having a challenge with uploading ofs transactions that failed in the first instance in t24 i. Reupload of Failed OFS transactions from Interswitch ii. Lock removal enhancement | I.T Digital Channels - Fintech | KCB - Information Technology | Biller Engine | Njuguna, Catherine | Scrum Leads | Otieno, Godfrey Okoth | 2024-09-18 | 2024-09-26 | Okodo, James | 16 | Active | Error Correction or Fixes ( RCA required ) | Channels and Cards |  | Allocated to Tribe |  |  | 11990 | User Story | C09189 - Interswitch Failing Upload of transactions & remove locks | Caroline Kathaaara <ken10904@kcbgroup.com> | New